Pilot Readiness Memo v0.2

RippleLogic / ripple.md / SGP for Nepal, Vietnam, and New Zealand

Status: Conditional GO for supervised Tier-2 pilots

Release line: RippleLogic v9.6.4 / ripple.md v2.2 / SGP v4.7.1 / Agent System v9.2 / Aligners Sheet v2.5

Prepared for: Bounded Tier-2 public-sector pilots in Nepal, Vietnam, and New Zealand

Date: 2026-05-01

Use boundary. This document is a pilot-planning artifact. It is not legal advice, does not replace local administrative law, and does not authorize automated or coercive public-sector action. Every jurisdiction-specific annex must be reviewed by qualified local legal, policy, and stakeholder reviewers before use.

# 1. Executive Summary

RippleLogic, ripple.md, and the Sentience Gradient Protocol are mature enough to support bounded, human-supervised Tier-2 government pilots in carefully selected public-sector contexts. The current release is strongest as a structured decision-support, audit, and learning framework. It should not be presented as an autonomous governance engine, a substitute for law, or a fully validated production deployment system.

The correct current posture is: GO for bounded pilots; NO-GO for autonomous deployment, coercive enforcement, Tier-4 claims, or full machine-complete validation claims.

# 2. Pilot-Grade vs Deployment-Grade

Approved pilot-grade claim: RippleLogic v9.6.4 is a structured, auditable, rights-floor and tail-risk-aware decision-support framework for supervised Tier-2 public-sector pilots.

Claims that must not be made:

Fully validated across jurisdictions.

Ready for unattended public-authority deployment.

A replacement for existing law, administrative review, judicial review, or human responsibility.

Tier-4 ProofPack complete.

SGP grants governance authority to any entity.

A successful workshop equals empirical validation.

# 3. Canonical Architecture to Preserve

Every pilot must preserve the order and non-compensatory logic of the canonical cascade. Any localization, simplification, workshop exercise, or public-facing summary must avoid collapsing these layers into a single score.

NCRC: Rights floors are non-compensatory. No welfare gain downstream may rescue a rights-floor failure.

TRC: Catastrophic and lock-in risks are bounded before ordinary welfare optimization.

Containment: Local gains must not degrade wider union scopes beyond permitted floors or escalation conditions.

RLS: Residual welfare ranking occurs only after admissibility gates pass.

UCI / HOI: Structural tie-break and diagnostic review apply where RLS is non-decisive or structural hollowing is live.

SGP boundary: SGP may inform protection and welfare-stream scaling but not governance authority or reductions in human rights.

ripple.md boundary: ripple.md wraps documentation, evidence, contestability, and assurance without weakening the canonical cascade.

# 4. Mandatory Pilot Boundary Conditions

Tier boundary: Phase 1 pilots must remain Tier 2.

Human authority boundary: Named human officials retain final decision authority.

Stakeholder boundary: Begin with all-human stakeholder cases.

Domain boundary: Use low-coercion, service-oriented, reversible public-sector cases first.

Documentation boundary: Every run must generate a Decision Note, PCC, reviewer signoff, and reflection date.

# 5. Recommended and Excluded Phase 1 Domains

## Recommended early domains

Public procurement.

Administrative service redesign.

Public digital-service review.

Infrastructure prioritization.

Education or health-service planning.

Environmental resilience planning.

Institutional AI adoption governance.

## Excluded Phase 1 domains

Policing and criminal justice.

Detention and incarceration.

Surveillance expansion.

Censorship or content restriction.

Immigration enforcement.

Emergency powers expansion.

Constitutional restructuring.

High-coercion welfare eligibility decisions.

# 6. Conditions Precedent to Launch

## Release-integrity conditions

One canonical artifact set selected and distributed.

Manifest regenerated from exact final bytes.

SHA-256 checksum file regenerated from exact final bytes.

No duplicate final, final-read, final-freeze, or upload-suffix variants distributed.

Workbook recalculated and saved before hashing.

Release-integrity or ProofPack Alpha package attached.

Public claim language bounded to supervised Tier-2 pilot status.

## Localization conditions

Country localization annex completed.

Local rights mapping completed and reviewed.

Recourse pathway mapped to actual institutions with power to review or remedy.

Subgroup and data-handling limits specified.

Translation and terminology review completed where relevant.

Excluded-domain list approved.

Escalation path named.

## Operational conditions

One completed sample Decision Note exists for the jurisdiction.

One completed sample PCC exists for the jurisdiction.

Reviewer chain and escalation chain are named.

Pilot-specific threat model completed.

Monitoring and NCAR reflection schedule approved.

Public-facing claim language approved before use.

# 7. Country Pilot Postures

## Nepal

Posture: Conditional GO

Best first pilots: Municipal service delivery, disaster resilience, procurement, education or health-service prioritization.

Special risks: Caste and Dalit harms, indigenous nationality and ethnicity, rural remoteness, disability, gender, disaster vulnerability, access to real recourse.

## Vietnam

Posture: Conditional GO with stricter exclusions

Best first pilots: Public-sector AI procurement, administrative digitization, workflow redesign, infrastructure or environmental resilience planning.

Special risks: Non-domination, meaningful review, information and privacy handling, public-authority concentration, surveillance or content-control risks.

## New Zealand

Posture: Conditional GO with Treaty-sensitive safeguards

Best first pilots: Local council planning, procurement, AI governance, infrastructure resilience, environmental planning.

Special risks: Te Tiriti / Treaty implications, iwi and hapu participation, natural justice, ECOL localization, privacy and official information.

# 8. Cross-Jurisdiction Risk Register

Capture risk: A ministry, agency, donor, or technical team frames scope, options, weights, or evidence to predetermine the result. Mitigation: Record scope rationale, excluded options, weight profile, reviewer signoff, and post-hoc changes.

Recourse theater: Appeal exists on paper but affected people cannot realistically use it. Mitigation: Require named authority, response timeline, remedy pathway, and usability testing.

Emergency shortcut drift: Emergency logic becomes routine. Mitigation: Require triage record, sunset date, post-hoc review, and frequency monitoring.

Translation drift: Key terms lose precision in local language or institutional translation. Mitigation: Maintain canonical English anchors and approved local glosses.

Selective use: Framework is invoked only when convenient. Mitigation: Define inclusion criteria and log excluded cases.

False validation: A successful workshop is described as proof of validity. Mitigation: Use pilot-tested and under evaluation language only.

Automation bias: Officials defer to the framework output as if it were authoritative. Mitigation: Require human rationale, disagreement logging, and ability to reject outputs.

Data misuse: Subgroup or sensitive data are collected beyond lawful need. Mitigation: Use data minimization and substitute harm-detection methods when needed.

# 9. Pilot Sequence

Phase 0, release and localization: freeze release set, complete annex, complete sample Decision Note and PCC, confirm review chain, approve claim language.

Phase 1, supervised pilot: run 3 to 5 real or near-real decisions, produce Decision Note and PCC for each, hold monthly NCAR review.

Phase 2, evaluation: compare with ordinary process, review clarity, burden, recourse, rights visibility, and stakeholder mapping, then expand, revise, narrow, or pause.

# 10. Pilot Success Criteria

Decision Notes completed before decisions.

PCCs reconstructable by an independent reviewer.

Rights-floor assumptions explicit and locally reviewed.

Tail-risk assumptions explicit.

Containment concerns visible and documented.

Recourse pathway real, not symbolic.

Emergency logic not normalized.

No rights-floor weakening occurs.

Participants report improved clarity rather than procedural confusion.

At least one meaningful policy or design improvement occurs because of unioning or ripple analysis.

# 11. Approved Public Claim Language

RippleLogic v9.6.4 is being piloted as a bounded Tier-2 governance decision-support framework, with ripple.md v2.2 and SGP v4.7.1 integrated at the documentation and assurance layer. The pilot tests structured rights-floor review, tail-risk review, containment reasoning, and auditable decision records in human-supervised public-sector settings. No Tier-3, Tier-4, autonomous deployment, or full production-validation claim is being made.

# 12. Final Recommendation

Proceed with bounded Tier-2 pilots in Nepal, Vietnam, and New Zealand only after the localization annex, sample Decision Note, sample PCC, reviewer chain, and pilot-specific threat model are complete. This posture is ambitious enough to generate real learning while conservative enough to protect public legitimacy and MathGov / RippleLogic credibility.

# Source Anchors for Reviewer Verification

These anchors help local reviewers verify the legal and institutional mapping. They are not a substitute for local legal advice or official counsel review.

Constitution of Nepal 2015: Official English PDF used as a source anchor for Part 3 fundamental rights and constitutional remedy review. URL: https://ag.gov.np/files/Constitution-of-Nepal_2072_Eng_www.moljpa.gov_.npDate-72_11_16.pdf

Constitution of the Socialist Republic of Vietnam 2013: English translation source anchor for reviewer convenience. Official Vietnamese legal texts and local legal review control for operational use. URL: https://constitutionnet.org/sites/default/files/tranlation_of_vietnams_new_constitution_enuk_2.pdf

New Zealand Bill of Rights Act 1990: Official legislation source anchor for NZ rights mapping. URL: https://www.legislation.govt.nz/act/public/1990/0109/latest/DLM224792.html

New Zealand Privacy Act 2020: Official legislation source anchor for personal information protection. URL: https://www.legislation.govt.nz/act/public/2020/0031/latest/LMS23223.html

New Zealand Official Information Act 1982: Official legislation source anchor for access to official information. URL: https://www.legislation.govt.nz/act/public/1982/0156/latest/whole.html

New Zealand Te Tiriti / Treaty guidance: Official policy source anchor for Treaty-sensitive public-sector policy work. URL: https://www.dpmc.govt.nz/publications/co-19-5-te-tiriti-o-waitangi-treaty-waitangi-guidance